## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Avinash Sutar Project plan
PROJECT PLAN
PROJECT NAME | Absence of insights for the relationship between student’s economic background, academic performance, competence and expected salary.
PROJECT MANAGER | Avinash Sutar
PROJECT DELIVERABLE | Project documentation , Code , Demo Video
PROJECT SCOPE
PROJECT START DATE | 2023-08-05
PROJECT END DATE | 2023-10-15
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify project problem |  | 2023-08-05 | 2023-08-05 | 1 | COMPLETED
| 1.2 Study problem |  | 2023-08-06 | 2023-08-06 | 1 | COMPLETED
| 1.3 Create a project charter |  | 2023-08-07 | 2023-08-07 | 1 | COMPLETED
| 1.4 Requirement gathering |  | 2023-08-08 | 2023-08-08 | 1 | COMPLETED
2 Planning
| 2.1 Create SRS |  | 2023-08-14 | 2023-08-16 | 2 | COMPLETED
| 2.2 Create WBS |  | 2023-08-15 | 2023-08-17 | 2 | COMPLETED
| 2.3 Create project plan |  | 2023-08-16 | 2023-08-18 | 2 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2023-08-20 | 2023-08-22 | 2 | COMPLETED
| 3.2 Build |  | 2023-08-21 | 2023-08-23 | 2 | COMPLETED
| 3.2.1 DATA |  | 2023-08-22 | 2023-08-24 | 2 | COMPLETED
| Clean data |  | 2023-08-25 | 2023-08-27 | 2 | COMPLETED
|  |  | 2023-08-29 | 2023-08-31 | 2 | COMPLETED
| Study problems |  | 2023-08-31 | 2023-09-02 | 2 | COMPLETED
| Import data |  | 2023-09-06 | 2023-09-08 | 2 | COMPLETED
| Design solution |  | 2023-09-19 | 2023-09-21 | 2 | COMPLETED
| Write conclusion |  | 2023-09-23 | 2023-09-25 | 2 | COMPLETED
| Project execution |  | 2023-09-29 | 31-09-2023 | 2 | COMPLETED
| 3.3 Testing |  | 2023-10-04 | 2023-10-06 | 2 | COMPLETED
3.3.1 Check for errors
| 4 Closure |  | 2023-10-10 | 2023-10-15 | 5 | COMPLETED